## Plan Progress as of 05092012
Task | Responsible | Start | End | Days | Complete |  | 2012-09-12 | 2012-09-13 | 2012-09-14 | 2012-09-15 | 2012-09-16 | 2012-09-17 | 2012-09-18 | 2012-09-19 | 2012-09-20 | 2012-09-21 | 2012-09-22 | 2012-09-23 | 2012-09-24 | 2012-09-25 | 2012-09-26 | 2012-09-27 | 2012-09-28 | 2012-09-29 | 2012-09-30 | 2012-10-01 | 2012-10-02 | 2012-10-03 | 2012-10-04 | 2012-10-05 | 2012-10-06 | 2012-10-07 | 2012-10-08 | 2012-10-09 | 2012-10-10 | 2012-10-11 | 2012-10-12 | 2012-10-13
[7 empty] | Wed | Thu | Fri | Sat | Sun | Mon | Tue | Wed | Thu | Fri | Sat | Sun | Mon | Tue | Wed | Thu | Fri | Sat | Sun | Mon | Tue | Wed | Thu | Fri | Sat | Sun | Mon | Tue | Wed | Thu | Fri | Sat
Prerequisites
Make something | Manny | 2012-09-14 | 2012-09-16 | 1 | 90% | 0.9
Do something | Moe | 2012-09-16 | 2012-09-18 | 2 | 100% | 2 | 2012-09-14: never enter data
Be somewhere | Jack | 2012-09-18 | 2012-09-30 | 9 | 100% | 9
POC Begins |  |  |  | 0 |  | 0
Start something | Manny, Moe | 2012-09-22 | 2012-09-24 | 1 | 100% | 1 | 2012-09-18: never enter data
Eat something | Jack | 2012-09-23 | 2012-09-27 | 4 | 65% | 2.6
Touch something | Manny, Jack | 2012-09-27 | 2012-10-05 | 7 | 55% | 3.85
Redo something | Jack | 2012-09-23 | 2012-09-23 | 0 | 0% | 0
Build something | Manny, Jack | 2012-09-24 | 2012-09-24 | 1 | 100% | 1
Look at something | Jack | 2012-09-25 | 2012-09-25 | 1 | 100% | 1
Wave at something | Manny | 2012-09-26 | 2012-09-26 | 1 | 70% | 0.7
Sneer at someone | Jack | 2012-09-27 | 2012-09-27 | 1 | 0% | 0
Break something inadvertantly | Manny, Moe | 2012-09-28 | 2012-09-28 | 1 | 0% | 0
Fix broken something | Manny, Moe | 2012-09-29 | 2012-09-29 | 0 | 0% | 0
Stack something's parts | Manny, Moe | 2012-09-30 | 2012-09-30 | 0 | 0% | 0
Apply duct tape to something | Manny, Moe | 2012-10-01 | 2012-10-01 | 1 | 50% | 0.5
Put something back on shelf | Manny, Moe | 2012-10-02 | 2012-10-02 | 1 | 0% | 0
Create a new standard for something | Manny, Moe | 2012-10-03 | 2012-10-03 | 1 | 0% | 0
Compile something | Manny, Moe | 2012-10-04 | 2012-10-04 | 1
Wave a flag at someone | Manny, Moe | 2012-10-05 | 2012-10-05 | 1 | 0% | 0
Push something too far | Manny, Moe | 2012-10-06 | 2012-10-06 | 0 | 0% | 0
Wave more flags at everyone | Manny, Moe | 2012-10-07 | 2012-10-07 | 0 | 0% | 0
|  |  |  | 34 | 66.32%
Today's Date | 2014-05-07 15:00 | 0%
Start Date | 2012-09-14
Projected End Date | 2012-10-07
Total Man Days | 34
Project Duration | 23
Your Project Name - Project Tracking

## Sheet2
Nonworking Date | Reason
2012-05-21 | MetLife Holiday
2012-05-22 | MetLife Holiday
2012-05-23 | MetLife Holiday
2012-05-24 | MetLife Holiday
2012-05-25 | MetLife Holiday
2012-05-28 | Memorial Day

## Sheet3
Legend
| Active Tasks | Tasks Overdue Start
| Completed Tasks (100%) | Tasks Running Late
| Non-Working Day | Non-Working Day
| Current Day | Current Day
Beyond Projected Last Day